## M365 Migration
M365 Migration Checklist
Please use the Notes columns to document file locations or where you are saving things
Item | Instructions | Pre Migration(Nov 5) | Notes | Post Migration (Nov 8) | Notes | Status
Mailbox Rules | Export Rules | Export rules and note where you saved them. |  | Import rules
Calendar Permissions | Calendar Permissions | Who have you given calendar permissions to? |  | Re-add these permissions using the Delegates function in M365
Delegate access | Delegate Access | Record who you have delegated access to for mailbox and calendar (note what permissions were assigned to your delegates) |  | Re-add the Delegates function in M365
Recurring Calendar Appointments |  | Recurring meeting requests will be "broken" and you will be missing the "Send Update" option. As a result, you will be unable to send updates to the meeting attendees. Therefore, it is recommended to take note of the existing recurring dates, times, locations, people invited and recurring frequency. Then recreate them as individual meetings and delete the series before the migration on November 5 |  | Re-create recurring meetings in M365 or leave them as individual meetings
Distribution Groups |  | Take note of any personal distribution groups you may have created |  | Recreate your personal distribution lists
Email Archives | Find Outlook Archives | Take note of where your email archives are stored |  | Refer to How to Re-Add Your Outlook Archives
Bookmarks |  | Take note of your bookmark link to email this will need to be updated |  | Update email bookmark | outlook.office.com
Email Signature | Email signature will need to be recreated in M365 email | You can copy it from a Sent Item or you can also copy it to a Word Document so that it keeps the format, then re-add it later or you can recreate it on the branding webpage. |  | Recreate your email signature | https://www.uwinnipeg.ca/branding/signature.html